## wavo_testing_report
Jira ID | Title | Description | Expected Result | Actual Result | Test Status | Screenshots
https://oaksol-team.atlassian.net/browse/WNA-60 | Incorrect UI for Video/Document header types | Previously, in Template Creation Header Type, when Video or Document was selected, the application displayed an incorrect media input option. Instead of the appropriate input field, the UI showed an incorrect media upload field. The issue has been fixed and testing was performed to verify that the correct Sample Media URL input field is displayed when Video or Document header types are selected during template creation. | When Header Type Video or Document is selected, the system should display the correct Sample Media URL input field instead of an incorrect media upload option. | The correct Sample Media URL input field is displayed for both Video and Document header types and functions as expected. | Pass | Wavo Evidence 1
https://oaksol-team.atlassian.net/browse/WNA-48 | Template & Quick Reply Cards | The Template and Quick Reply screens were updated to display only the relevant details on the template cards to improve clarity and user experience. Unnecessary or extra information was removed so that users can easily view important details on each card. Testing was performed to verify that only the required information is displayed on the template and quick reply cards and that the behaves correctly. | Template and Quick Reply cards should display only relevant details and maintain a clean. | The cards display only the required information and the appears clear and consistent across both screens. | Pass
https://oaksol-team.atlassian.net/browse/WNA-62 | Quick Reply Screen Structure | The Quick Reply screen was verified to ensure that its structure and available fields match the web implementation. During testing, all fields, layout, and options were compared with the web version to confirm consistency across platforms. The Quick Reply screen displayed the correct structure and included all required fields as expected in the web implementation. No discrepancies were found during verification. | The Quick Reply screen structure and available fields should match the web implementation. | The Quick Reply screen structure and fields matched the web implementation correctly. | Pass | Wavo Evidence 1
https://oaksol-team.atlassian.net/browse/WNA-44 | Sidebar and Wavo setup | The Sidebar and Wavo Setup functionalities were tested to ensure that all sections, options, and navigation items are displayed and functioning correctly. During testing, the sidebar menu structure and the Wavo setup configuration were verified to confirm that all required items load properly and work as expected. The navigation between sidebar options and Wavo setup sections worked smoothly without any errors or issues. | The Sidebar and Wavo Setup should display all required sections and options correctly, and users should be able to access and navigate them without any issues. | All Sidebar menus and Wavo Setup options were displayed correctly, and navigation worked properly without errors. | Pass
https://oaksol-team.atlassian.net/browse/WNA-54 | Quick Reply Button Height and UI | The Quick Reply feature, button height adjustments, back button redirection, and UI improvements were tested to ensure proper functionality and design consistency. Button styling, language selection dropdown, back navigation, and input field UI worked correctly across all template screens. However, the EmojiPicker component in the TemplateFormScreen was not functioning properly, and emojis could not be inserted as expected. | All UI improvements should work correctly, including button styling, back button redirection, language selection dropdown, and the EmojiPicker component should allow users to select and insert emojis. | All UI improvements worked as expected, but the EmojiPicker component was not functioning correctly. | Fail | Wavo Evidence 1